## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Repo + Spring Boot skeleton + DB connection (pair-programmed, whole team) | MUST HAVE | No Dependency | Kathan, Geethika, Harshith, Hari | 3- Completed
S1 | S1 | US-002 | Design shared entities: Beneficiary, Scheme, User, Role (Module 1 foundation) | MUST HAVE | US-001 | Kathan | 3- Completed
S1 | S1 | US-003 | Finalize API contract - endpoint names & request/response shapes, documented in API-CONTRACT.md | MUST HAVE | US-002 | Kathan, Geethika, Harshith, Hari | 3- Completed
S1 | S1 | US-004 | GitHub repo setup - collaborators, branch protection (PR + 1 approval required on main) | SHOULD HAVE | No Dependency | Kathan, Geethika, Harshith, Hari | 3- Completed
S2 | S2 | US-005 | Module 1 - Beneficiary registration, document upload, scheme master data CRUD | MUST HAVE | US-002 | Kathan | 3- Completed
S2 | S2 | US-006 | Module 2 - Eligibility scoring engine | MUST HAVE | US-002 | Geethika | 3- Completed
S2 | S2 | US-007 | Module 2 - Multi-level verification workflow (field officer / district officer / finance approver routing) | MUST HAVE | US-006 | Geethika | 3- Completed
S2 | S2 | US-008 | Module 3 - Early disbursement plan structure scaffolding (core logic deferred until verification is stable) | COULD HAVE | US-007 (soft) | Harshith | 2- In Progress
S3 | S3 | US-009 | Milestone 3 - Staged disbursement plan & schedule engine (DisbursementPlan, DisbursementStage, ApplicationDisbursementSchedule; stage % must sum to 100) | MUST HAVE | US-007 | Kathan | 3- Completed
S3 | S3 | US-010 | Milestone 3 - Compliance milestone tracking & reminders (ComplianceMilestone entity, due-date calc, @Scheduled overdue job, mark-complete -> release-next-stage hook) | MUST HAVE | US-009 | Geethika | 3- Completed
S3 | S3 | US-011 | Milestone 3 - Fund utilization & regional analytics (read-only): fundUtilizationByScheme/Region, budgetExhaustionWarnings, nonComplianceAnalysis, approvalTurnaroundTime | MUST HAVE | US-009, US-010 | Harshith | 3- Completed
S3 | S3 | US-012 | Milestone 3 - DashboardController (8 endpoints under /api/v1/dashboard/*) and ReportService (Apache POI Excel, OpenPDF PDF exports) | MUST HAVE | US-011 | Hari | 3- Completed
S3 | S3 | US-013 | Milestone 3 - dashboard/index.html with Chart.js + mock AnalyticsDataSource, swappable via @Primary bean | MUST HAVE | US-012 | Hari | 3- Completed
S3 | S3 | US-014 | Milestone 3 - end-to-end integration test suite: Plan -> Schedule -> Compliance -> Analytics -> Reports | MUST HAVE | US-009, US-010, US-011, US-012 | Hari | 3- Completed
S3 | S3 | US-015 | Module 3 gap resolution - dueDateOffsetDays made user-editable; overdue milestones surfaced in admin panel + beneficiary dashboard banner | SHOULD HAVE | US-010 | Hari | 3- Completed
S4 | S4 | US-016 | Milestone 4 - Security & RBAC: Spring Security config, auth/token endpoints, User/Role/Permission entities, centralized URL-pattern authorization rules | MUST HAVE | No Dependency | Kathan | 3- Completed
S4 | S4 | US-017 | Milestone 4 - Audit logging framework: AuditLog entity, AOP interceptor on verification/approval/disbursement methods, filterable admin query API | MUST HAVE | US-016 (soft, role names) | Geethika | 3- Completed
S4 | S4 | US-018 | Milestone 4 - REST API integrations: Treasury client (mock fund-release/confirmation) and Beneficiary registry client, retry/error handling, Phase-3 hook into M3 disbursement flow | MUST HAVE | No Dependency | Hari | 3- Completed
S4 | S4 | US-019 | Milestone 4 - Deployment & docs: Dockerfile/docker-compose, application-prod.yml, Swagger/OpenAPI, CI pipeline skeleton, performance pass | MUST HAVE | No Dependency | Harshith | 3- Completed
S4 | S4 | US-020 | Milestone 4 - full end-to-end suite (login -> verify -> disburse -> treasury call -> audit entry -> analytics) + compiled final documentation | MUST HAVE | US-016, US-017, US-018 | Harshith | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 176 | 63 | 57 | 32 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Repo, Spring Boot + Hibernate + DB connection setup (whole team, pair-programmed) | 2026-06-30 | 2026-07-01 | Kathan, Geethika, Harshith, Hari | Others | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | Design shared entities: Beneficiary, Scheme, User, Role | 2026-07-02 | 2026-07-04 | Kathan | Design | 3- Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 3 | Finalize API contract (endpoint names, request/response shapes) into API-CONTRACT.md | 2026-07-06 | 2026-07-10 | Kathan, Geethika, Harshith, Hari | Others | 3- Completed | 6 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG (WEEKS 3-4: MODULE 1 & 2)
US-005 | 1 | Beneficiary registration, document upload, scheme master CRUD | 2026-07-13 | 2026-07-17 | Kathan | Coding | 3- Completed | 12 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 2 | Eligibility scoring engine | 2026-07-13 | 2026-07-16 | Geethika | Coding | 3- Completed | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 3 | Multi-level verification workflow (field/district officer, finance approver routing) | 2026-07-17 | 2026-07-22 | Geethika | Coding | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 4 | Disbursement plan structure scaffolding (early start) | 2026-07-20 | 2026-07-22 | Harshith | Design | 2- In Progress | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG (MILESTONE 3 - WEEKS 5-6)
US-009 | 1 | Staged disbursement plan & schedule engine; stage % validated to sum to 100 | 2026-07-27 | 2026-07-29 | Kathan | Coding | 3- Completed | 10 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 2 | Compliance milestone tracking, due-date calc, @Scheduled overdue-flagging job | 2026-07-29 | 2026-07-31 | Geethika | Coding | 3- Completed | 9 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | 3 | Fund utilization & regional analytics (read-only aggregation queries) | 2026-07-30 | 2026-08-01 | Harshith | Coding | 3- Completed | 8 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 4 | DashboardController (8 endpoints) + ReportService (Apache POI Excel, OpenPDF PDF) | 2026-08-01 | 2026-08-03 | Hari | Coding | 3- Completed | 10 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 5 | dashboard/index.html with Chart.js + mock AnalyticsDataSource | 2026-08-04 | 2026-08-04 | Hari | Build | 3- Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | 6 | Milestone 3 end-to-end test suite: Plan -> Schedule -> Compliance -> Analytics -> Reports | 2026-08-05 | 2026-08-06 | Hari | Integration Test | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | 7 | Module 3 gap resolution - dueDateOffsetDays editable, overdue milestone admin panel & dashboard banner | 2026-08-06 | 2026-08-07 | Hari | Coding | 3- Completed | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG (MILESTONE 4 - WEEKS 7-8)
US-016 | 1 | Security & RBAC - Spring Security config, auth/token endpoints, centralized URL-pattern authorization | 2026-08-10 | 2026-08-13 | Kathan | Coding | 3- Completed | 12 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | 2 | Audit logging framework - AuditLog entity, AOP interceptor on verification/approval/disbursement methods | 2026-08-11 | 2026-08-14 | Geethika | Coding | 3- Completed | 10 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | 3 | Treasury integration scaffold - IntegrationStatus, RetryExecutor (exponential backoff), mock treasury controller | 2026-08-10 | 2026-08-11 | Hari | Coding | 3- Completed | 9 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | 4 | Beneficiary registry integration - client interfaces, 3-attempt retry, @SpringBootTest with TestSecurityConfig | 2026-08-12 | 2026-08-13 | Hari | Integration Test | 3- Completed | 8 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | 5 | Phase-3 hook wiring treasury client into existing Milestone 3 disbursement release flow | 2026-08-14 | 2026-08-14 | Hari | Integration Test | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | 6 | Dockerfile/docker-compose, application-prod.yml, Swagger/OpenAPI, CI pipeline skeleton | 2026-08-10 | 2026-08-13 | Harshith | Build | 3- Completed | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | 7 | End-to-end suite (login -> verify -> disburse -> treasury -> audit -> analytics) + final compiled docs | 2026-08-17 | 2026-08-21 | Harshith | System Test | 2- In Progress | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Needed to confirm exact shared-entity fields before Persons 1-3 could branch off independently | Held a 30-min sync to lock Section 4 shared contracts (Application entity fields, seed scheme) before anyone branched
Sprint 2 | Day 4 | Module 3 scaffolding depended on 'what does an approved verification look like' from Module 2 | Coordinated with Geethika (Module 2 owner) on the completed-verification contract before scaffolding disbursement structure
Sprint 3 | Day 1 | Disbursement stage percentages needed validation to guarantee they sum to exactly 100% | Kathan added save-time validation rejecting invalid stage configurations before they reach the database
Sprint 3 | Day 2 | Compliance 'mark complete -> release next stage' handshake needed to be locked before either side coded | Kathan and Geethika agreed the exact interface (method name/params) on day one of Milestone 3
Sprint 3 | Day 3 | Analytics queries span Kathan's and Geethika's tables, not fully mergeable until Thursday | Harshith developed and tested analytics against seed/mock data matching the agreed schema until the merge
Sprint 3 | Day 4 | Apache POI Excel export threw errors on merged header cells | Rebuilt the report template using CellStyle objects instead of manual cell merges
Sprint 4 | Day 1 | Audit query API's admin-only restriction needed exact role name constants from the RBAC module | Kathan published role name constants on day one; Geethika built and tested the query API open, then added the role check last
Sprint 4 | Day 2 | Treasury/beneficiary hook risked a mid-week merge conflict if wired into Milestone 3 code too early | Defined the integration interface early but deferred wiring into the disbursement release flow to Phase 3, as planned
Sprint 4 | Day 5 | End-to-end suite (login through analytics) couldn't be attempted until Security, Audit, and Integrations all existed | Harshith pulled each teammate's branch daily during independent development to avoid a cold final-day integration

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 (Foundation) | 2026-06-30 | 2026-07-10 | Kathan, Geethika, Harshith, Hari | Locking shared contracts (entity fields, API shapes) in a single day-one sync | Letting anyone start a module before the shared entities were merged | Reviewing every PR with at least one person outside the module | Tagged the Week-2 checkpoint in dev once shared entities + skeleton were stable, then everyone pulled fresh
2 | Sprint 2 (Module 1 & 2) | 2026-07-13 | 2026-07-22 | Kathan, Geethika, Harshith, Hari | Running a 10-min daily standup even over chat | Starting Module 3/4 scaffolding without confirming the Module 2 completed-verification contract first | Keeping each person strictly inside their own Java package to avoid merge conflicts | Demoed to each other and merged dev into main at the Week-4 checkpoint
3 | Sprint 3 - Milestone 3 | 2026-07-27 | 2026-07-29 | Kathan | Validating stage percentages sum to 100% before persisting a disbursement plan | Hardcoding a fixed stage count instead of keeping it configurable per scheme | Wrapping schedule generation and stage-release in @Transactional methods | Locked the stage-release interface with Geethika before either side wrote code
4 | Sprint 3 - Milestone 3 | 2026-07-29 | 2026-07-31 | Geethika | Using LocalDate/LocalDateTime consistently on a single agreed timezone (IST) | Wiring reminders to a real SMTP/SMS service instead of logging them | Making the daily overdue-flagging job idempotent | Verified the overdue job doesn't double-flag milestones when run twice in a day
5 | Sprint 3 - Milestone 3 | 2026-08-01 | 2026-08-06 | Hari | Testing report exports against real seed data early, not just at the end | Leaving the Chart.js dashboard wiring until the last day | Keeping the analytics data source swappable via an @Primary mock bean | Rebuilt the Excel export template after CellStyle-based merges replaced manual ones
6 | Sprint 4 - Milestone 4 | 2026-08-10 | 2026-08-14 | Hari | Building and testing both external clients against their own mocks from day one | Wiring the treasury hook into Milestone 3 code before Phase 3, risking a mid-week conflict | Logging every outbound call and its outcome to feed the audit trail | Deferred the disbursement-flow hook to Phase 3 exactly as planned, avoiding a merge conflict
7 | Sprint 4 - Milestone 4 | 2026-08-17 | 2026-08-21 | Kathan, Geethika, Harshith, Hari | Pulling each teammate's branch daily during independent development | Waiting until the final day to attempt the end-to-end suite | Merging in the agreed order - Security first, then Audit/Integrations, Deployment last | Kept a running risk log during integration to decide what to descope if anything couldn't be fixed in time